Part IX: Sport and Recreational Management

Worksheet V

- Example of “Time Factors”

Graduating-Class Basketball and Badminton Tournament Schedule

XXXXXX Secondary School 2012-2013 Graduating-Class Basketball and Badminton Tournament Preparatory Work Schedule Basketball Competition Date; ：; 30/11/2012, 7/12/2012, 14/12/2012 (Friday). Badminton Competition Date; ：; 10/12/2012 (Monday). No; Item; Expected Date; Officer-in-charge. 1; Set up a working committee; 3/10/2012; aaa. 2; Work out rules and regulations, design posters; 17/10/2012; bbb. 3; Invite guests; 17/10/2012; xxx(Teacher). 4; Start promotion; 22/11/2012; ddd eee. 5; Application; 8/11/2012; xxx(Teacher). 6; Conduct fixture draw; 9/11/2012; xxx(Teacher). 7; Prepare Competition Schedule; 13/11/2012; ccc. 8; Invite referees and volunteers; 13/11/2012; xxx(Teacher). 9; Print and distribute competition schedule; 15/11/2012; bbb. 10; Arrange tasks for each member on competition days; 15/11/2012; aaa. 11; Train referees and volunteers; 20/11/2012; xxx(Teacher). 12; Arrange photographers and video shooters on competition days; 23/11/2012; xxx(Teacher). 13; Prepare prizes and medals; 26/11/2012; xxx(Teacher). 14; Prepare souvenirs for guests and testimonials for referees and volunteers; 26/11/2012; xxx(Teacher). 15; Prepare equipment; 26/11/2012; xxx(Teacher). 16; Announce the final results; 18/12/2012; aaa. 17; Arrange evaluation meetings and filing; 19/12/2012; xxx(Teacher). 18; Run a prize presentation ceremony; 20/12/2012; bbb.

2. Question

Prepare a work schedule for an inter-house basketball competition in your school.